 -
 -
 -
Click and enter a value from the list of items
Click and enter a value from the list of items
Click and enter a value from the list of items
Click and enter a value from the list of items
 -
 -
 -
 -
 -
 -
 -
 -
## Product Backlog
Planned Sprint	Actual Sprint	US ID	User Story Description	MOSCOW	Dependency	Assignee	Status
Sprint 1	Sprint 1	US001	As a data engineer, I want to collect and clean Azure usage data so that it becomes ready for demand forecasting.	MUST HAVE	Dataset availability	Backend	3- Completed
Sprint 2	Sprint 2	US002	As a data scientist, I want to engineer demand-driving features such as seasonality indicators, lag variables, and usage trends so that the dataset becomes suitable for machine learning models.	MUST HAVE	Cleaned dataset	Backend	3- Completed
Sprint 3	Sprint 3	US003	As a data scientist, I want to train ARIMA and XGBoost models using the cleaned data so that I can compare their forecasting accuracy.	MUST HAVE	Feature engineered dataset	Backend	3- Completed
Sprint 3	Sprint 3	US004	As a data scientist, I want to evaluate model performance using metrics like MAE and RMSE so that the best forecasting model can be selected.	MUST HAVE	Trained Model	Backend	3- Completed
Sprint 4	Sprint 4	US005	As a developer, I want to deploy the forecasting model so that Azure demand predictions can be generated automatically.	SHOULD HAVE	Selected model	Backend	1- Not Started
Sprint 4	Sprint 4	US006	As a developer, I want to integrate the predictions into a dashboard so that the Azure supply team can monitor demand trends.	COULD HAVE	Deployed model	Frontend	1- Not Started

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID	Task ID	Task Description	Task Start Date	Task Completion Date	Team Member	Activity	Status	Original Estimate Effort (In Hours)	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Day 8	Day 9	Day 10	Day 11	Day 12	Day 13	Day 14
					54	1	2	3	3	4	4	4	3	3	2	2	2	2	1
US001	T1	Collect Azure service usage dataset with regional and timestamp information for demand forecasting	6-Feb-26	8-Feb-26	Backend	Data Collection	3- Completed	5	1	1	1
US001	T2	Clean and validate dataset by handling missing values, removing duplicates and standardized formats	9-Feb-26	12-Feb-26	Backend	Data Cleaning & Validation	3- Completed	4		1	1	1	1
US002	T3	Integrate external variables such as economic trends, market demand trends	20-Feb-26	23-Feb-26	Backend	Feature Engineering	3- Completed	4			1	1	1	1
US002	T4	Create lag variables and seasonality indicators for time series forecasting	24-Feb-26	27-Feb-26	Backend	Feature Engineering	3- Completed	4				1	1	1	1
US003	T5	Train ARIMA model using historical Azure usage data	5-Mar-26	7-Mar-26	Backend	Model Training	3- Completed	8					1	1	1
US003	T6	Train XGBoost model for demand forecasting	08-Mar-26	10-Mar-26	Backend	Model Training	3- Completed	8					1	1	1
US004	T7	Evaluate models using MAE and RMSE to compare performance	11-Mar-26	13-Mar-26	Backend	Model Evaluation	3- Completed	4					1	1	1
US004	T8	Select best performing model for forecasting	14-Mar-26	15-Mar-26	Backend	Model Selection	3- Completed	3					1	1
US005	T9	Deploy forecasting model for demand prediction pipeline	20-Mar-26	24-Mar-26	Backend	Model Deployment	1- Not Started	4					1	1	1	1	1
US006	T10	Integrate predictions into visualization dashboard	25-Mar-26	29-Mar-26	Frontend	Dashboard Integration	1- Not Started	10					1	1	1	1	1

## Stand up Meeting
Sprint	Day	Impediments	Action Taken
Sprint 1	Day 2	Missing values and inconsistent records in dataset	Cleaned dataset, removed duplicates and standardized column formats
Sprint 2	Day 1	Identifying important features influencing resource demand	Analyzed dataset and selected operational and economic indicators
Sprint 2	Day 3	Difficulty capturing temporal demand patterns	Created lag variables, rolling statistics, and seasonality features
Sprint 3	Day 2	Understanding suitable forecasting models for demand prediction	Studied ARIMA and XGBoost models and their applicability
Sprint 3	Day 4	Handling categorical data and model training errors	Encoded categorical variables and successfully trained models
Sprint 4	Day 2	Difficulty integrating forecasting outputs with capacity planning workflow	Standardized prediction output format and connected model results to planning dashboard

## Retrospection
SL #	Sprint #	Sprint start date	Sprint end date	Team member name	Start Doing	Stop Doing	Continue Doing	Action taken
1	Sprint 1	02-02-2026	16-02-2026	Backend	Document dataset structure and preprocessing steps clearly	Ignoring missing values during early analysis	Validating dataset consistency before modeling	Created structured data preprocessing workflow
2	Sprint 2	16-02-2026	02-03-2026	Backend	Implement systematic feature engineering for demand patterns	Adding unnecessary features that increase complexity	Testing engineered features before model training	Finalized lag features and seasonality indicators
3	Sprint 3	02-03-2026	16-03-2026	AI Team	Apply hyperparameter tuning for machine learning models	Training models without performance comparison	Evaluating models using MAE and RMSE metrics	Selected best-performing forecasting model
4	Sprint 4	16-03-2026	30-03-2026	Backend + Frontend	Prepare forecasting outputs for capacity planning insights	Waiting until final stage for integration testing	Reviewing model predictions with visualization	Integrated forecasting results into planning workflow
5
6
7